## Title
Project title | Husky Air
Project Performance Calculations
Project members(Group 8) | Gouri Patil( Z1931431)
Manisha Reddy Bandala ( Z1949511 )
Megha Sudha Aluru(Z1947069)
Course number and name | OMIS 690 - Information Technology Project Management
Professor | Prof. John Pendergrass
Northern Illinois University
Date | 2022-07-28

## Calculations
Name |  | Equation | Calculated Value | Result interpretation
Length of the project | Group 8 | 8+7 | 15 weeks
BAC |  |  | 300000
Planned Value (PV) |  | BAC * progress = 300000 * 0.5 | 150000
Earned Value (EV) |  | 45% of BAC = 0.45 * 300000 | 135000
Actual Cost (AC) |  | BAC * progress * (1+%above/below plan) = 300000 * 0.5* 1.15 | 172500
CPI |  | EV/AC = 135000/172500 | 0.78 | Since the CPI<1, the projectis less efficient.
SPI |  | SPI = EV / PV= 135000/150000 | 0.9 | Since the SPI<1, the project is behind the schedule.
EAC (CPI and SPI) |  | EAC = AC + [(BAC - EV) / (CPI * SPI)] EAC = 172500+ [(300000 – 135000)/ (0.78*0.9)] | 407543
Over Budget Percentage |  | ((EAC – BAC) / (BAC)) * 100 = ((407543 – 300000) / (300000)) * 100 | 35.8% | Project is around 36 % over the budget, $107543 over the budget value of $300K
BAC (Revised) |  | BAC + 10% of BAC => BAC + (BAC *10/100) 300000 + (300000 * 10/100) | $330,000
TCPI (BAC Vaild) |  | (BAC – EV) / (BAC-AC) = (330000 - 135000) / (330000 - 172500) | 1.238 | Since TCPI is greater than 1.0, it is difficult to complete the project with the provided budget.