## Title
Project title | Husky Air
Project members | Gouri Patil( Z1931431)
Manisha Reddy Bandala ( Z1949511 )
Megha Sudha Aluru(Z1947069)
Course number and name | OMIS 690 - Information Technology Project Management
Professor | Prof. John Pendergrass
Northern Illinois University
Date | 2022-06-30

## WBS Dictionary
WBS Level | WBS Code | WBS Name | WBS Description | Resources | Due Date | Hours
1 | 1 | Project Management Planning | The project management team oversees determining how to complete a task within a specific time frame, generally with key phases and resources. | Megha Sudha Aluru | 2022-06-29 | 64
2 | 1.1 | Requirement gathering | The process of determining the precise requirements of your project from start to finish. | Megha Sudha Aluru | 2022-06-20 | 8
3 | 1.1.1 | Project Charter | A project charter should only have three aspects: team leader, scope, and tasks. Following the approval of the charter, you should develop a project plan. | Megha Sudha Aluru | 2022-06-21 | 8
3 | 1.1.2 | Scope Management Plan | A project manager develops the scope within which the project and its deliverables are defined | Megha Sudha Aluru | 2022-06-22 | 8
3 | 1.1.3 | Schedule Management Plan | The schedule management plan is developed that specifies how the schedule for a project will be developed, controlled, and inspected. | Megha Sudha Aluru | 2022-06-23 | 8
3 | 1.1.4 | Budget Allocation Plan | A project budget is the total amount of money set aside for the project's specific purpose over a set period. Budget management aims to keep project costs within the agreed budget while meeting project objectives. | Megha Sudha Aluru | 2022-06-24 | 8
| 1.1.5 | WBS and RTM plan | Breaking the tasks into smaller work packages that require equal efforts and developing requirments. | Megha Sudha Aluru | 2022-06-28 | 12
3 | 1.1.6 | Risk Management Plan | It is the method of trying to identify, analyzing, and managing risk to a task that could impact the desired results. | Megha Sudha Aluru | 2022-06-29 | 12
1 | 2 | Design Architecture | As project managers, architects create strategies, layouts, and designs that fulfil the needs of consumers while following to any applicable codes. In addition, they provide project deadlines, budgets, and documentation. | Gouri Patil | 2022-07-08 | 56
2 | 2.1 | Back-end Design | The database access level of software or hardware that includes any feature that requires digital access and navigation. | Gouri Patil | 2022-06-30 | 8
2 | 2.2 | Front-end Design | The front-end phase of a project begins with the development of a project concept and ends with the final decision to fund the project. Front-end management's ultimate goal is to improve the right strategic perspective. | Gouri Patil | 2022-07-01 | 16
3 | 2.1.1 | ER diagram | The entity relationship model is depicted in a diagram known as the er diagram (ERD). This information architecture diagram is designed to illustrate our understanding of data. This concept is then applied in the creation and testing of business solutions. | Gouri Patil | 2022-07-05 | 4
3 | 2.1.2 | Database Diagram | The process database is a permanent collection of entire project performance data; it must be used for project planning, forecasting, productivity and customer satisfaction analysis, and other activities. | Gouri Patil | 2022-07-05 | 4
3 | 2.2.1 | Flow chart | A flow chart is a visual help for defining the procedures you intend to use to complete the project. The diagram demonstrates the interrelated and parallel processes that occur throughout the project's life cycle. | Gouri Patil | 2022-07-06 | 8
3 | 2.2.2 | Page Layout | It is task for arranging the visual elements of web pages. It includes text, images, buttons and other items in the header, footer and body section. | Gouri Patil | 2022-07-07 | 8
3 | 2.2.3 | Content creation | Content creation is the source of information to any multimedia, specifically digital content, for the purpose of a final in specific situations. | Gouri Patil | 2022-07-08 | 8
1 | 3 | Code Implementation | This task includes the implementation of logic to run the application. It involves interaction between the elements using the programming languages. | Manisha Reddy Bandala | 2022-07-15 | 208
2 | 3.1 | Database creation | It is the task of creating the database, and tables, and copying data from files to the tables. | Manisha Reddy Bandala | 2022-07-11 | 8
2 | 3.2 | web-based interface | It is the user interface designed for the web application of Husky Air. The user will access this application using a browser. | Manisha Reddy Bandala | 2022-07-13 | 16
3 | 3.1.1 | Data storage | Data storage administration refers to the software and methods that increase the performance of information storage. It may contain virtualization technology, replica, duplication, privacy, compression, reduction, web filtering, automation systems, storage management, and virtual memory. | Manisha Reddy Bandala | 2022-07-20 | 40
3 | 3.1.2 | Query Development | queries or statements are an issue in SQL, and also in any programming. One process for creating lengthy inquiries is to start small and gradually extend or develop the query of interest. | Manisha Reddy Bandala | 2022-07-25 | 40
3 | 3.2.2 | Application Logic | A conceptual framework of how a project is perceived or intended to contribute to its set results is characterized as project logic. It prioritizes outcomes above methods. It shows the causal relationships between inputs, actions, outputs, and outcomes. | Manisha Reddy Bandala | 2022-08-01 | 40
3 | 3.2.3 | Integration with database | Database integration is the process of collecting information from multiple sources (such as digital networking, IoT tracking devices, data stores, present in the data, and others) and sharing a current document of it throughout an organization. | Manisha Reddy Bandala | 2022-08-05 | 40
3 | 3.3.1 | Mobile-optimized development | It is a task where application logic and UI are optimized to match the mobile interface. | Manisha Reddy Bandala | 2022-08-15 | 24
1 | 4 | Testing Records | Project records are the only tool for retaining traceability of multiple decisions and choices made throughout the course of a project. | Gouri Patil | 2022-08-16 | 176
2 | 4.1 | Unit Testing | Unit testing is a software development method of analyzing the integration tests parts of an application, referred to as units, individually and independently for proper operation. | Gouri Patil | 2022-08-24 | 40
3 | 4.1.1 | Integration testing | Integration testing is a sort of testing that evaluates the interactions of multiple elements, the way modules connect into a single system, and code comply with the requirements. | Gouri Patil | 2022-08-31 | 40
3 | 4.1.2 | System testing | System testing is stated as testing a complete and fully integrated software product. These criteria for the project under black-box testing, in which knowledge of the inner concept of the code is not needed and is performed by the testing team. | Megha Sudha Aluru | 2022-09-08 | 48
3 | 4.1.3 | User Acceptance testing | User Acceptance Testing ensures that the project's solution satisfies the functional and non-functional criteria provided in the business requirements. UAT may also indicate issues that were not stated in the BRD, such as interface issues. | Megha Sudha Aluru | 2022-09-15 | 48
1 | 5 | Go-Live | An enterprise technology program's go-live is the result of weeks, months, and often years of research, planning and scheduling, preparation, implementation, management, and controls including a company's specific stakeholders. | Manisha Reddy Bandala | 2022-09-19 | 80
2 | 5.1 | Enivornment Setup | A project environment is all of the different factors that affect your project work. These are external and internal factors that might affect your project's duration, cost, team spirit, and more. | Manisha Reddy Bandala | 2022-09-26 | 40
2 | 5.2 | Production Deployment | Deployment plans define the objectives, schedule, and process for deploying project deliverables. Deliverables might be a software upgrade, new employee training, or even your next travel schedule. | Manisha Reddy Bandala | 2022-09-30 | 40
1 | 6 | Documents | The project charter document is the most critical component of documentation in the Project Initiation stage. This is essential since it gives you the ability to support as project leader for the project. | Megha Sudha Aluru | 2022-10-03 | 240
2 | 6.1 | Technical manual | A technical document is a designed to make it simple for the end-user to know the technical elements of utilizing a service or product. | Megha Sudha Aluru | 2022-10-21 | 150
2 | 6.2 | User manual | A user manual is a document that is presented to a user to assist them in operating a specific system business, or service effectively. | Megha Sudha Aluru | 2022-11-10 | 90

## RTM
Requirements Traceability Matrix
Project Title: Husky Air
Date: 6/30/2022
Req ID | Requirement description | Business justification | Source | WBS Task | Test Strategy | Status
1 | Login Page | A user must be able to successfully login with a valid username and password. | Megha Sudha Aluru | 2.2,2.2.2 | Verify if a user can successfully login with a valid username and password. | Pending
2 | Website Content | A user must be able to access the application's main page and its contents as designed. | Gouri Patil | 2.2.3 | Test to see if a user can access the application's main page and its contents as designed. | Pending
3 | Data storage | The information entered about the patients and pilots must be stored. | Manisha Reddy Bandala | 3.1.1 | Check if the information entered about the patients and pilots is stored. | Pending
4 | Search for available pilots | The application must display available pilots at that time. | Gouri Patil | 3.2.2 | Verify if the application displays available pilots at that time. | Pending
5 | Patient's page to view their information | The patient's total information must be displayed when we enter their name and ID number. | Manisha Reddy Bandala | 3.2.2 | Verify if the patient's total information is displayed when we enter their name and ID number. | Pending
6 | Add/Edit page to update patient-pilot information | User must be able to change the patients' information on the Add/Edit page. | Megha Sudha Aluru | 3.2.2 | Check to see if we can change the patients' information on the Add/Edit page. | Pending
7 | Mobile optimized interface | The mobile UI must have all of the features which are operational. | Megha Sudha Aluru | 3.1.1 | Check the mobile UI to see whether all of the features are operational. | Pending
8 | UAT environment for testing | User Acceptance Testing environment must be up and running. | Megha Sudha Aluru | 4.1,4.2,4.3,4.4 | Verify by running a couple of the above test cases to ensure that the User Acceptance Testing environment is up and running. | Pending
9 | Azure environment setup to host/deploy application | The Azure environment setup must be up and running to host/deploy for a web application. | Megha Sudha Aluru | 5.1 5.2 | Check if the Azure environment setup is up and running to host/deploy for a web application. | Pending
10 | Technical manual | The technical documentation must contain all application-related abbreviations, as well as its design and operation. | Megha Sudha Aluru | 6.1 | Verify and ensure that the technical documentation contains all application-related abbreviations, as well as its design and operation. | Pending
11 | User manual | The user manual must contain all the application-related operations and is simple to comprehend. | Megha Sudha Aluru | 6.2 | Verify and ensure that the user manual contains all application-related operations and is simple to comprehend. | Pending

## Risk Register
RISK REGISTER
PROJECT TITLE |  |  | COMPANY | PROJECT MANAGER |  |  |  |  | DATE
Automated Husky Air |  |  | Husky Air | Kara Allen |  |  |  |  | 2022-07-26
Ref ID | Risk Description | Risk Justification/Cause | Risk Category | Probability | Impact | Priority | Owner | Strategic action
1 | Project delay due to scope creep. | Scope creep can be one of the causes to deliver the project late. | Project Management Risk | Medium | High | 1 | Project Manager | Allocating the extra/buffer time for the critical changes in the scope management plan will help resolve the delay issues. Scheduling tools can be used.
2 | Data security breach | The sensitive information can be leaked, stolen, or the application can be hacked. | Technical Risk | Low | High | 1 | Team developer | Implementing the function asking for regular change of password, building secure 'https' server and paying attention to physical security.
3 | Unavailibility of company's official personnal(resources) |  | Organizational Risk | Low | High | 1 | Project Manager
4 | Project exceeding the estimated budget |  |  | Medium | High | 1 | Project Manager
5 | Conflicts between the teammates and communication issues |  | Project Management Risk | Medium | High | 2 | Project Manager
6 | Updates in the technology or software. |  |  |  |  | 1
7 | Performance issues of the application |  |  |  |  | 1
8 | Critical team member dropping out |  | Operational Risk |  |  | 2